## Sprint 1 – Planning Board
Sprint 1 – Planning Board
User Story | Epic | Acceptance Criteria Summary | Story Points | Assignee (Suggested) | Notes / Dependencies
As a new customer, I must provide Ghana Card details during registration so the company can verify my identity. | EPIC 6: Customer Registration & Verification | Ghana Card number validation, photo upload, secure storage | 5 | Backend Dev / Frontend Dev | Requires Ghana Card API or mock service
As the system, I must securely store Ghana Card data in compliance with data protection laws. | EPIC 8: Technical & Compliance | Encrypted storage, audit log, GDPR-style retention | 3 | Backend Dev | Ties directly into Ghana Card registration
As the system, I must comply with PCI-DSS for card payments to prevent data breaches. | EPIC 8: Technical & Compliance | Prepare infrastructure for secure card data processing, tokenization ready | 3 | DevOps / Backend | No storage of card data; plan for Flutterwave
As a user, I want cement batch numbers on invoices so I meet safety compliance. | EPIC 8: Technical & Compliance | Batch number included in order + invoice data model | 2 | Backend Dev | Needs to be included in DB schema early
As one of the first 20 customers, I want special incentive packages so I’m rewarded for early adoption. | EPIC 6: Customer Registration & Verification | Incentive logic: first 20 users trigger discount flag | 3 | Backend Dev / Frontend Dev | Logic triggers in Sprint 2; tracking setup now
Set up CI/CD pipelines for development, staging, and production | Foundation (Infra) | Pipelines for backend/frontend microservices | 3 | DevOps | GitHub Actions or GitLab CI, Docker
Set up API Gateway and service routing (Auth, Product) | Foundation (Infra) | Gateway routes traffic to microservices securely | 5 | Backend Dev / DevOps | Connects React frontend to services
Initialize project architecture (monorepo, service folders, structure) | Foundation (Infra) | Project structure aligned with microservice architecture | 2 | Full Stack Dev | Align to ERD and service diagram
Design & deploy database schema from ERD | Foundation (Infra) | All major tables + foreign keys initialized | 5 | Backend Dev | ERD from blueprint should match models
Create user registration form with Ghana Card fields | EPIC 6 | Frontend form, error validation, mobile-first design | 3 | Frontend Dev / UI/UX | Coordinates with backend logic
Create test plan and test environment | QA Setup | Prepare QA base: auth tests, test cases, coverage | 2 | QA Engineer | Align with Sprint 1 scope and EPIC 6
Create brand system and integrate assets | Brand/UX (Foundation) | Logo, colors, fonts, component guide | 2 | UI/UX Designer | Setup for reuse across modules
📊 Sprint Summary
Category | Count | Story Points
Functional (User Stories) | 5 | 16
Technical Tasks | 6 | 20
Total | 11 | 36

## Sprint 2 – Planning Board
Sprint 2 – Planning Board
Sprint Goal: Build the complete product catalog (materials + services), finalize Ghana Card verification, implement customer profile management, and enable basic search & filter and early adopter incentives.
User Story | Epic | Acceptance Criteria Summary | Story Points | Assignee (Suggested) | Notes / Dependencies
As a customer, I want to browse products by category with filters so I can find materials fast. | EPIC 1: Order Management System | Product list with filter by ≥3 attributes (e.g., category, brand, type) | 5 | Frontend Dev / Backend Dev | Uses product catalog API; Jumia-style UI
As a customer, I want to search materials by brand or type so I don't scroll endlessly. | EPIC 1: Order Management System | Search bar with auto-suggestions + keyword matching | 3 | Frontend Dev | Connected to catalog search endpoint
As a contractor, I want tiered bulk pricing applied automatically so I get volume discounts. | EPIC 1: Order Management System | ≥100 units triggers 1.5% discount on key products | 5 | Backend Dev | Business logic in pricing engine
As a user, I want one-click reordering from order history so I save time. | EPIC 1: Order Management System | "Reorder" feature duplicates past cart in ≤3 clicks | 3 | Frontend / Backend Dev | Requires order history to be functional
As a customer, I want to book consultancy services (e.g., architectural drawings) so I get professional support. | EPIC 5: B2B Contractor Portal & Services | Service booking UI, consultant calendar, requirements form | 5 | Frontend / Backend / UI/UX | Service models are part of catalog
As a verified customer, I want to receive birthday/holiday greetings with special offers. | EPIC 6: Customer Registration & Verification | Auto detection of birthday/holiday + promo offer | 2 | Backend Dev / QA | Integrate with user profile data
As one of the first 20 customers, I want special incentive packages so I'm rewarded for early adoption. | EPIC 6: Customer Registration & Verification | System tracks early registrations, applies flags | 2 | Backend Dev | Continue from Sprint 1 logic
Build customer profile management (edit info, view history) | EPIC 6: Customer Registration & Verification | Update profile, view orders, change password | 3 | Frontend / Backend Dev | CRUD for user profile
Ghana Card verification: final integration and live test | EPIC 6: Customer Registration & Verification | Full validation flow, photo upload, API/live test | 5 | Backend Dev / QA | Must pass test scenarios
Create product and service catalog UI | EPIC 1 + 5 | Material & service cards, category views, responsiveness | 4 | Frontend Dev / UI/UX | Requires data API from backend
Develop catalog APIs for materials + services | EPIC 1 + 5 | GET endpoints for products/services, pagination, filter params | 4 | Backend Dev | Integrates with DB schema from Sprint 1
Optimize DB for catalog filtering/search | Technical | Indexing for performance
📊 Sprint 2 Summary
Category | Count | Story Points
Functional (User Stories) | 9 | 32
Technical Tasks | 4 | 12
Total | 13 | 44